## Oncoming Features List
NFS-GANESHA : list of features to be add to the product			January, 21 2009

	Security Features	Workload	Deadline	Status
	Finalize RPCSEC_GSS support with krb5’s gssrpc	in progress		Done 0.99.43
	Implement RPCSECGSS support with librpcsec_gss	2 weeks
	Validate TI-RPC’s implementation of RPCSEC_GSS	2 weeks

	FSAL	Workload	Deadline	Status
	Add corrrect “su” in FSAL_PROXY with RPCSEC_GSS	4 days
	FSAL on top of LUSTRE	heavy		beta 0.99.52
	FSAL on top of FSAL/DMU	Internship ?
	FSAL on top of ZFS	heavy
	Optimize and stress FSAL_PROXY	1 week		beta 0.99.52
	FSAL on top of Ext2 (via LOFS)	1 month	31/03/09	in progress
	FSAL_POSIX port to MySQL	1 month	31/01/09	Done 0.99.51
	FSAL on top of PVFS2	Internship ?

	NFS implementation	Workload	Deadline	Status
	OP_OPEN4 prefetch the file / OP_CLOSE4 could dispose the file	3 days
	Implement correct NFS4ERR_DELAY and / NFS3ERR_JUKEBOX	1 day
	Coherency in case of multi nfsd for a single // namespace	Internship ?
	attribute fs.location (multiple servers, load balancing)	1 week
	READ delegations	heavy
	WRITE delegations	wait for client
	DRC for seqid	1 month
	Makes FSAL_XAttrs tunable by user via sqlite.	1 month
	Attributes for extended attributes objects	2 weeks		in progress
	“ghost directory” to manage extended attributes	1 week		Done 0.99.42

	Internals	Workload	Deadline	Status
	coherency for the errors in between the different layers	3 days
	NFSv4 state machine to be cleaned up	1 week		Done 0.99.44
	Metadata writeback	heavy		Beta 0.99.51
	dump for the md cache	heavy
	Versions and snapshots	heavy
	datacache used LOFS to produce big files	1 month
	Use nodesets supports in Configuration file	1 week		Done 0.99.43
	(HPSS) LOFS’s big files staged and migrated on demand	1 week

	Interoperability	Workload	Deadline	Status
	TI-RPC support to be added and validated	2 weeks		Done 0.99.44
	Ipv6 support via TI-RPC	1 week		Done 0.99.45
	Port to FreeBSD and BSD variants	1 week		Done 0.99.50
	Port to FreeBSD and BSD variants	2 months		Done 0.99.50
	Test with FreeBSD clients (vmware)	1 week
	Test with Solaris / OpenSolaris clients (vmware)	1 week
	Test with Windows clients (NFS Maestro)	2 weeks
	Compile on a PowerPC Linux Box	3 weeks		Done 0.99.49

	Publications	Workload	Deadline	Status
	WiP Topic for FAST’09, abstract	1 day	27/01/09	Done